## sheet1
BUYER CODE | PO STATUS | PO TYPE | LPO | BPO | ORD DT | ORD ENTRY DATE | DELV DT | DISP DT | PLANNED PROD START DT | PLANNED PROD END DT | HOLIDAYS | AVL. DAYS | PLANNED FIN.COM DT | ORD UNIT | PO AREA | PO AREA SQ YD | ITEM NAME | QUALITY | DESIGN | SHAPE | COLOR | OSIZE | MAP SIZE | ORD QTY | TAG PCS | TOT ISS QTY | TOT ISS DUE | TOT BAZAR QTY | TOT BAZAR DUE | IN HS PLAN QTY | IN HS ISS | IN HS ISS DUE | IN HS BZR QTY | IN HS BZR BAL | OS PLAN QTY | OS ISS | OS ISS DUE | OS BZR QTY | OS BZR BAL | UNDER FINISHING | FINISHED QTY | DISP QTY | DISP DUE | PACKED_TO_OTHER | PACKED_FROM_OTHER | CHAMPO BUYER CODE ORDER NO DELIVERY DATE
BI-01 | COMPLETED | REGULAR | L 296 | 10-Oct-23 | 2023-10-10 | 2023-10-19 | 2023-12-30 | 2023-12-30 |  |  | 0 | 0 |  | Ft | 5777.72 | 568.75 | HAND TUFTED | TP | RS-005 | REC | MULTI | 1.08x2.08 | 1.08x2.08 | 1300 | 0 | 1300 | 0 | 1300 | 0 | 1300 | 1300 | 0 | 1300 | 0 | 0 | 0 | 0 | 0 | 0 | 1300 | 0 | 0 | 1300 | 0 | 0
BI-01 | COMPLETED | REGULAR | L 296 | 10-Oct-23 | 2023-10-10 | 2023-10-19 | 2023-12-30 | 2023-12-30 |  |  | 0 | 0 |  | Ft | 5777.72 | 568.75 | HAND TUFTED | TP | RS-008 | REC | MULTI | 1.08x2.08 | 1.08x2.08 | 1300 | 0 | 1300 | 0 | 1300 | 0 | 1300 | 1300 | 0 | 1300 | 0 | 0 | 0 | 0 | 0 | 0 | 1300 | 0 | 0 | 1300 | 0 | 0
BI-01 | COMPLETED | REGULAR | L 296 | 10-Oct-23 | 2023-10-10 | 2023-10-19 | 2023-12-30 | 2023-12-30 |  |  | 0 | 0 |  | Ft | 5333.28 | 525 | HAND TUFTED | TP | RS-101 | REC | DARK BLUE | 1.08x2.08 | 1.08x2.08 | 1200 | 0 | 1200 | 0 | 1200 | 0 | 1200 | 1200 | 0 | 1200 | 0 | 0 | 0 | 0 | 0 | 0 | 1200 | 0 | 0 | 1200 | 0 | 0
BI-01 | COMPLETED | REGULAR | L 296 | 10-Oct-23 | 2023-10-10 | 2023-10-19 | 2023-12-30 | 2023-12-30 |  |  | 0 | 0 |  | Ft | 5333.28 | 525 | HAND TUFTED | TP | RS-102 | REC | BLUE | 1.08x2.08 | 1.08x2.08 | 1200 | 0 | 1200 | 0 | 1200 | 0 | 1200 | 1200 | 0 | 1200 | 0 | 0 | 0 | 0 | 0 | 0 | 1200 | 0 | 0 | 1200 | 0 | 0
BI-01 | COMPLETED | REGULAR | L 296 | 10-Oct-23 | 2023-10-10 | 2023-10-19 | 2023-12-30 | 2023-12-30 |  |  | 0 | 0 |  | Ft | 5333.28 | 525 | HAND TUFTED | TP | RS-103 | REC | BLUE | 1.08x2.08 | 1.08x2.08 | 1200 | 0 | 1200 | 0 | 1200 | 0 | 1200 | 1200 | 0 | 1200 | 0 | 0 | 0 | 0 | 0 | 0 | 1200 | 0 | 0 | 1200 | 0 | 0
BI-01 | COMPLETED | REGULAR | L 296 | 10-Oct-23 | 2023-10-10 | 2023-10-19 | 2023-12-30 | 2023-12-30 |  |  | 0 | 0 |  | Ft | 6444.38 | 634.375 | HAND TUFTED | TP | RS-104 | REC | PINK/MULTI | 1.08x2.08 | 1.08x2.08 | 1450 | 0 | 1450 | 0 | 1450 | 0 | 1450 | 1450 | 0 | 1450 | 0 | 0 | 0 | 0 | 0 | 0 | 1450 | 0 | 0 | 1450 | 0 | 0
BI-01 | COMPLETED | REGULAR | L 296 | 10-Oct-23 | 2023-10-10 | 2023-10-19 | 2023-12-30 | 2023-12-30 |  |  | 0 | 0 |  | Ft | 6444.38 | 634.375 | HAND TUFTED | TP | RS-105 | REC | BLUE/MULTI | 1.08x2.08 | 1.08x2.08 | 1450 | 0 | 1450 | 0 | 1450 | 0 | 1450 | 1450 | 0 | 1450 | 0 | 0 | 0 | 0 | 0 | 0 | 1450 | 0 | 0 | 1450 | 0 | 0
BI-01 | COMPLETED | REGULAR | L 296 | 10-Oct-23 | 2023-10-10 | 2023-10-19 | 2023-12-30 | 2023-12-30 |  |  | 0 | 0 |  | Ft | 6444.38 | 634.375 | HAND TUFTED | TP | RS-106 | REC | MULTI | 1.08x2.08 | 1.08x2.08 | 1450 | 0 | 1450 | 0 | 1450 | 0 | 1450 | 1450 | 0 | 1450 | 0 | 0 | 0 | 0 | 0 | 0 | 1450 | 0 | 0 | 1450 | 0 | 0
BI-01 | COMPLETED | REGULAR | L 296 | 10-Oct-23 | 2023-10-10 | 2023-10-19 | 2023-12-30 | 2023-12-30 |  |  | 0 | 0 |  | Ft | 6444.38 | 634.375 | HAND TUFTED | TP | RS-107 | REC | NAVY | 1.08x2.08 | 1.08x2.08 | 1450 | 0 | 1450 | 0 | 1450 | 0 | 1450 | 1450 | 0 | 1450 | 0 | 0 | 0 | 0 | 0 | 0 | 1450 | 0 | 0 | 1450 | 0 | 0
BI-01 | COMPLETED | REGULAR | L 296 | 10-Oct-23 | 2023-10-10 | 2023-10-19 | 2023-12-30 | 2023-12-30 |  |  | 0 | 0 |  | Ft | 6222.16 | 612.5 | HAND TUFTED | TP | RS-109 | REC | MULTI | 1.08x2.08 | 1.08x2.08 | 1400 | 0 | 1400 | 0 | 1400 | 0 | 1400 | 1400 | 0 | 1400 | 0 | 0 | 0 | 0 | 0 | 0 | 1400 | 0 | 0 | 1400 | 0 | 0
BI-01 | COMPLETED | REGULAR | L 296 | 10-Oct-23 | 2023-10-10 | 2023-10-19 | 2023-12-30 | 2023-12-30 |  |  | 0 | 0 |  | Ft | 6222.16 | 612.5 | HAND TUFTED | TP | RS-110 | REC | MULTI | 1.08x2.08 | 1.08x2.08 | 1400 | 0 | 1400 | 0 | 1400 | 0 | 1400 | 1400 | 0 | 1400 | 0 | 0 | 0 | 0 | 0 | 0 | 1400 | 0 | 0 | 1400 | 0 | 0
BI-01 | COMPLETED | REGULAR | L 296 | 10-Oct-23 | 2023-10-10 | 2023-10-19 | 2023-12-30 | 2023-12-30 |  |  | 0 | 0 |  | Ft | 6222.16 | 612.5 | HAND TUFTED | TP | RS-111 | REC | MULTI | 1.08x2.08 | 1.08x2.08 | 1400 | 0 | 1400 | 0 | 1400 | 0 | 1400 | 1400 | 0 | 1400 | 0 | 0 | 0 | 0 | 0 | 0 | 1400 | 0 | 0 | 1400 | 0 | 0
BI-01 | COMPLETED | REGULAR | L 296 | 10-Oct-23 | 2023-10-10 | 2023-10-19 | 2023-12-30 | 2023-12-30 |  |  | 0 | 0 |  | Ft | 5777.72 | 568.75 | HAND TUFTED | TP | RS-006 | OVAL | MULTI | 1.08x2.08 | 1.08x2.08 | 1300 | 0 | 1300 | 0 | 1300 | 0 | 1300 | 1300 | 0 | 1300 | 0 | 0 | 0 | 0 | 0 | 0 | 1300 | 0 | 0 | 1300 | 0 | 0
BI-01 | COMPLETED | REGULAR | L 296 | 10-Oct-23 | 2023-10-10 | 2023-10-19 | 2023-12-30 | 2023-12-30 |  |  | 0 | 0 |  | Ft | 5777.72 | 568.75 | HAND TUFTED | TP | RS-007 | OVAL | BLUE | 1.08x2.08 | 1.08x2.08 | 1300 | 0 | 1300 | 0 | 1300 | 0 | 1300 | 1300 | 0 | 1300 | 0 | 0 | 0 | 0 | 0 | 0 | 1300 | 0 | 0 | 1300 | 0 | 0
BI-01 | COMPLETED | REGULAR | L 296 | 10-Oct-23 | 2023-10-10 | 2023-10-19 | 2023-12-30 | 2023-12-30 |  |  | 0 | 0 |  | Ft | 5777.72 | 568.75 | HAND TUFTED | TP | RS-009 | OVAL | PINK | 1.08x2.08 | 1.08x2.08 | 1300 | 0 | 1300 | 0 | 1300 | 0 | 1300 | 1300 | 0 | 1300 | 0 | 0 | 0 | 0 | 0 | 0 | 1300 | 0 | 0 | 1300 | 0 | 0
BI-01 | COMPLETED | REGULAR | L 296 | 10-Oct-23 | 2023-10-10 | 2023-10-19 | 2023-12-30 | 2023-12-30 |  |  | 0 | 0 |  | Ft | 5777.72 | 568.75 | HAND TUFTED | TP | RS-010 | OVAL | BLUE/PINK | 1.08x2.08 | 1.08x2.08 | 1300 | 0 | 1300 | 0 | 1300 | 0 | 1300 | 1300 | 0 | 1300 | 0 | 0 | 0 | 0 | 0 | 0 | 1300 | 0 | 0 | 1300 | 0 | 0
BI-01 | COMPLETED | REGULAR | L 296 | 10-Oct-23 | 2023-10-10 | 2023-10-19 | 2023-12-30 | 2023-12-30 |  |  | 0 | 0 |  | Ft | 8750 | 962.5 | HAND TUFTED | TP | RS-108 | ROUND | MULTI | 2.06x2.06 | 2.06x2.06 | 1400 | 0 | 1400 | 0 | 1400 | 0 | 1400 | 1400 | 0 | 1400 | 0 | 0 | 0 | 0 | 0 | 0 | 1400 | 0 | 0 | 1400 | 0 | 0